## Shopenzer Testcases
|  |  |  | Date | 2022-11-15
|  |  |  | Team ID | PNT2022TMID20125
|  |  |  | Project Name | Project -Customer Care Registry
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Commnets | Executed By
LoginPage_TC_OO1 | Functional | Agent Register Page | The Registered User will not be able to register again | NIL | 1.Enter URL and click go 2.Click on My Account dropdown button 3.Goto Register Page | NIL | Registered user will not be able to register again | Working as expected | Pass | Successful | AJAY
LoginPage_TC_OO2 | UI | Agent Register Page | Verify the UI elements in Register page popup | HTML,FLASK,CSS | 1.Enter URL and click go 2.Click on My Account dropdown button 3.Verify Register page popup with below UI elements: a.email text box b.password text box c.Register button | NIL | Application should show below UI elements: a.email text box b.password text box c.Username text box c.Register button | Working as expected | Pass | Successful | GOKULAKRISHNAN
LoginPage_TC_OO3 | Functional | User Register Page | The Registered User will not be able to register again | NIL | 1.Enter URL and click go 2.Click on My Account dropdown button 3.Goto Register Page | Username: gokul password: gokul123 | The registered user will not able to register again | Working as expected | Pass | Successful | ARSHAD PARVEZ
LoginPage_TC_OO4 | UI | User Register Page | The Registered User will not be able to register again | NIL | 1.Enter URL and click go 2.Click on My Account dropdown button 3.Goto Register Page | Username: gokul@gmail password: gokul123 | Already registered will pop up as the alert message | Working as expected | Pass | Successful | YUTHA MESAK
LoginPage_TC_OO5 | UI | Agent Profile page | The agents profile page should be displayed | HTML,FLASK,CSS | 1.Enter URL and click go 2.Click on My Account dropdown button 3.Enter Valid username/email in Email text box 4.Enter valid password in password text box 5.Click on login button 6.Goto profile. | Username: agent password: agent123 | The profile page of agent should be displayed | Working as expected | Pass | Successful | AJAY
LoginPage_TC_OO6 | UI | User Profile page | The profile page of user will be displayed | HTML,FLASK,CSS | 1.Enter URL and click go 2.Click on My Account dropdown button 3.Enter Valid username/email in Email text box 4.Enter valid password in password text box 5.Click on login button 6.Goto profile. | Username:User123 Password:1234 | The profile page of user should be displayed | Working as Expected | Pass | Successful | GOKULAKRISHNAN
LoginPage_TC_OO7 | UI | Admin Pofile page | The profile page of admin will be displayed | HTML,FLASK,CSS | 1.Enter URL and click go 2.Click on My Account dropdown button 3.Enter Valid username/email in Email text box 4.Enter valid password in password text box 5.Click on login button 6.Goto profile. | Username:Admin123 Password:3456 | The profile page of admin should be displayed. | Working as Expected | Paas | Successfull | ARSHAD PARVEZ
LoginPage_TC_OO8 | UI | User Ticket RAaised PAge | The user's raised ticket should be displayed | HTML,FLASK,CSS | 1.Enter URL and click go 2.Click on My Account dropdown button 3.Enter Valid username/email in Email text box 4.Enter valid password in password text box 5.Click on login button 6.View Raised ticket | Username:User123 Password:1234 | The raised ticket of the user will be displayed | Working as Expected | Pass | Successful | YUTHA MESAK
LoginPage_TC_OO9 | Functional | User Ticket RAaised PAge | The user must be able to raise the ticket | NIL | 1.Enter URL and click go 2.Click on My Account dropdown button 3.Enter Valid username/email in Email text box 4.Enter valid password in password text box 5.Click on login button 6.View Raised ticket | Username:User123 Password:1234 | The user must be able to raise a ticket. | Working as Expected | Pass | Successful | AJAY
LoginPage_TC_OO10 | UI | User Ticket RAaised PAge | The user must be able to view all the tickets raised | HTML,FLASK,CSS | 1.Enter URLand click go 2.Click on My Account dropdown button 3.Enter Valid username/email in Email text box 4.Enter valid password in password text box 5.Click on login button 6.View Raised ticket. 7.View all the tickets | Username:User123 Password:1234 | The user must be able to view all the tickets raised | Working as Expected | pass | Successful | GOKULAKRISHNAN
LoginPage_TC__OO11 | Functional | User Ticket RAaised PAge | The user must press view all tickets button to view all tickets raised | NIL | 1.Enter URL and click go 2.Click on My Account dropdown button 3.Enter Valid username/email in Email text box 4.Enter valid password in password text box 5.Click on login button 6.View Raised ticket. 7.View all the tickets | Username:User123 Password:1234 | The user must be able to view all the tickets raised | Working as expected | Pass | Successful | ARSHAD PARVEZ